## Module Dashboard
Preckon - completion by module
Every feature verified against the codebase and the deployed database on 20 Aug 2026. Weighted: Done 1.0, Partial 0.5, Scaffolded 0.25, Missing 0.
Module | What it does | Features | Done | Partial | Missing | % Complete | Progress | Where it stands
TenderLogix | Tender engineering and bid orchestration | 18 | 5 | 7 | 6 | 47.2% | █████████░░░░░░░░░░░ | Lifecycle, bid decision and approval work end to end. Requirements-with-citation and the compliance matrix - the module's core promise - are only partly there.
DocLogix | CDE, document control and document intelligence | 15 | 11 | 2 | 2 | 80% | ████████████████░░░░ | Built out on 20 Aug from 23%. Register, numbering, revisions, transmittals, revision diff, retrieval, review, distribution and retention all work and are deployed. The honest limit: most of it is reachable only through the API, and OCR is absent.
DrawLogix | Drawing, design, BIM and drawing intelligence | 16 | 7 | 5 | 4 | 59.4% | ████████████░░░░░░░░ | The strongest module. Intake, viewer, takeoff, revision compare and the AI copilot all work. Recognition, IFC and clash are the gaps.
QuantLogix | Takeoff, quantities and BOQ | 11 | 5 | 3 | 3 | 59.1% | ████████████░░░░░░░░ | Measurement, BOQ and reconciliation are solid. source_region now exists, so the headline click-a-quantity-see-the-drawing claim is unblocked at the data layer - takeoff still has to write the regions.
CostLogix | Rates, estimating and commercial | 8 | 1 | 1 | 6 | 18.8% | ████░░░░░░░░░░░░░░░░ | Pricing works. Everything after award - budget, commitments, forecast, EVM - is not started.
ScheduleLogix | Scheduling and project time intelligence | 15 | 4 | 0 | 11 | 26.7% | █████░░░░░░░░░░░░░░░ | A real deterministic CPM engine exists. The migration-first mission - P6 import, calendars, baselines - is entirely unbuilt.
ProcureLogix | Packages, RFQs and procurement | 6 | 1 | 0 | 5 | 16.7% | ███░░░░░░░░░░░░░░░░░ | Package grouping works. RFQ, quotes and commitments are not started.
NarrativeLogix | Technical narrative and proposal writing | 3 | 2 | 1 | 0 | 83.3% | █████████████████░░░ | Small module, largely complete for what it claims.
Platform / Core | Identity, tenancy, audit, AI governance, operations | 40 | 19 | 9 | 12 | 58.8% | ████████████░░░░░░░░ | Trust foundations are strong, and AI governance now exists: policy, budgets, model registry, cache safety and a per-attempt ledger. The gaps left are enterprise identity (SSO, MFA, SCIM), operational maturity (CI, staging, backup) and finishing the wiring of what was just built.
ValueLogix | Value engineering: alternatives, impact, approval, benefit | 16 | 0 | 0 | 16 | 0% | ░░░░░░░░░░░░░░░░░░░░ | Specified in unusual depth (PEB chapter 35, 20 documents) and built nowhere - no module key, no tables, no artifact type. The specification already covers everything, including continuous detection (Value Radar) and the AI-proposes-human-approves boundary. This is implementation work, not design work.
Engineering Bible | PEB - the 477-document specification the platform is built against | 11 | 8 | 2 | 1 | 81.8% | ████████████████░░░░ | 477 documents across 28 chapters, with governance, quality gates and its own CI. The gap is not coverage but connection: no code cites a chapter, and nothing records which chapters are implemented - so the Bible cannot answer what is left to build.
TOTAL | All modules | 159 | 63 | 30 | 66 | 49.1% | ██████████░░░░░░░░░░ | Against the blueprints as written. These describe a platform the documents themselves budget a large team for.

## TenderLogix
TenderLogix - 47% complete
Tender engineering and bid orchestration. 18 features audited: 5 done, 7 partial, 6 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Lifecycle | Tender workspace and lifecycle states | Done | lifecycle.ts, pursuit.ts, project lifecycle endpoint; workflow.tenderlogix + 5 sub-workflows seeded. | - | P0 | -
Lifecycle | Bid / no-bid decision | Done | bid_decision artifact type; agent.bid_qualification; workflow.bidqualification. | - | P0 | -
Lifecycle | Bid approval gate | Done | bid_approval artifact type; agent.approval_prep; bid.approve permission on Owner role. | - | P0 | -
Intake | Tender document intake and summary | Done | tender_summary artifact type; agent.tender; workflow.classify. | - | P0 | -
Requirements | Requirements extraction with clause citation | Partial | spec_clause artifact type + agent.specification extract normative clauses. | Clauses are extracted but are not turned into tracked Requirement objects with owner, due date, response and status. | P0 | L
Requirements | Compliance matrix | Partial | compliance_item artifact type; agent.compliance and agent.compliance_lead. | No matrix view, no mandatory flag, no Requirement-Evidence-Response-Approval chain. | P0 | L
Scope | Scope breakdown and gap detection | Missing | None. | Specified-but-unpriced, drawing-without-BOQ and duplicate-scope detection all absent. | P1 | L
BOQ | Employer vs derived vs adopted quantity reconciliation | Done | boq/reconcile.ts - 4 verdicts, proportional tolerance with absolute floor, override trail. 27 tests. | Logic complete but NOT yet surfaced in the BOQ screen. | P1 | S
Clarifications | Clarification lifecycle | Partial | client_query artifact type; agent.clarification; workflow.clarificationloop. | No Draft-Review-Approved-Submitted-Answered-Impact-Closed state machine; impact assessment not enforced before close. | P1 | M
Addenda | Addendum intelligence and impact | Missing | None. | Unincorporated mandatory addendum must be a hard submission blocker. Not modelled at all. | P1 | L
Risk | Risk register and commercial positions | Partial | risk artifact type; agent.risk; agent.commercial; workflow.riskreview. | No assumptions/qualifications/exclusions register, no risk-adjusted margin. | P1 | M
Strategy | Bid strategy and scenarios | Missing | None. | Target/minimum margin, walk-away conditions, competitor assumptions absent. | P2 | M
Submission | Submission readiness score | Partial | submission.ts; lifecycle gates. | Weighted readiness exists; the separate HARD GATE (blockers) is not implemented. | P1 | M
Submission | Submission builder and manifest | Partial | proposal_doc artifact type; agent.proposal; workflow.bidassembly. | No manifest validation (revision, signature, naming, format, addendum acknowledgement); no revision freeze at submission. | P1 | M
War Room | Tender War Room cockpit | Partial | surfaces/tender.tsx; project dashboards. | No countdown, readiness tiles, blocker list or AI brief. | P2 | M
Negotiation | Negotiation / BAFO revisions | Missing | None. | - | P2 | M
Award | Award / loss capture and win-loss analytics | Missing | None. | - | P2 | M
Handover | Bid-to-project handover | Missing | None. | Award should transfer to downstream modules with no re-keying. | P2 | L

## DocLogix
DocLogix - 80% complete
CDE, document control and document intelligence. 15 features audited: 11 done, 2 partial, 2 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Repository | File storage and binary versioning | Done | file + file_page; document_revision.file_version bumps when the file is replaced without the revision changing. | - | P0 | -
Register | Intelligent document register (35+ controlled fields) | Done | document_register - number, title, type, discipline, originator, volume, level, zone, package, confidentiality, status, retention, required_by. Registers before a file exists. | API only - no register screen yet. | P0 | M
Numbering | Document numbering engine | Done | numbering.ts - schemes as data, segment validation, reserved ranges, sequence allocation, legacy adoption. Duplicates blocked by a unique index, not an app check that races. 33 tests. | - | P0 | -
Revisions | Formal revision vs file version | Done | revision.ts - alpha/numeric/ISO 19650, I and O skipped, C outranks P, supersession planned then applied atomically. 32 tests. | - | P0 | -
Revisions | Revision intelligence (change classification) | Done | compare.ts - deterministic LCS diff over extracted text, classified as dimension/requirement/commercial/reference/note, significant-first review order. 28 tests. | Text only. Drawing-geometry diff is cad/compare.ts; the two are not yet joined into one report. | P1 | M
Workflow | Configurable document workflow | Partial | document_review with stage, min_approvals, due_at; contractual response codes; issue gate. 44 tests with review.ts. | No escalation, no reminders, no conditional branching. The SLA date exists and nothing acts on it. | P1 | M
Review | Review and approval workspace | Partial | document_review + document_review_assignee + document_comment; comments pinned to a source_region, threaded, blocking flag; decision log. | Backend complete, no UI. A reviewer cannot reach any of it without an API client. | P1 | L
Transmittals | Transmittal management | Done | transmittal + item + recipient; carries revisions not documents; sending freezes; acknowledgements; recall never deletes. 35 tests. | API only - no transmittal screen. | P0 | M
Extraction | Specification clause extraction | Done | spec_clause artifact type; agent.specification; surfaces/specs.tsx. | - | P0 | -
Extraction | OCR for scanned documents | Missing | CAD extraction handles drawings only. | No OCR for scanned PDFs, Office formats, email or images. Anything not already text-extracted is invisible to search. | P1 | L
Search | Semantic / natural-language project search | Done | retrieval.ts + index-store.ts - meaning-based chunking, hybrid ranking, budget packing, revision-aware. The chunk table finally has a writer. 34 tests. | No embeddings generated yet, so ranking is lexical plus identifier matching. The column and the cosine function are ready for them. | P0 | M
Provenance | Document-region provenance anchor | Done | source_region - page, polygon, text range or model object, cited by entity_type/entity_id, with method and confidence. | - | P0 | -
Distribution | Distribution lists and controlled issue | Done | distribution_list + distribution_member with to/cc, applies_to filters for when a list is offered. | - | P1 | -
Retention | Retention categories and legal hold | Done | retention.ts - hold outranks retention including expired retention; live references block; no policy is not permission. Nothing deletes, it answers whether deletion is permitted. | - | P1 | -
UI | Screens for register, review, transmittals and search | Missing | surfaces/drawings.tsx still renders the old file list. | Everything built today is reachable only through the API. This is the honest limit on calling the module done. | P0 | L

## DrawLogix
DrawLogix - 59% complete
Drawing, design, BIM and drawing intelligence. 16 features audited: 7 done, 5 partial, 4 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Intake | DWG / DXF / PDF intake | Done | cad_extraction, file_page; Python sidecar with LibreDWG dwg2dxf; SVG render pipeline. | - | P0 | -
Intake | IFC import and export | Missing | None. | IFC is the open-BIM requirement named in three documents. No import or export at all. | P1 | L
Viewer | Drawing viewer with pan, zoom, layers | Done | cad/editor.tsx, cad/viewport.tsx; 31 sheets live in production. | - | P0 | -
Recognition | Symbol and object recognition to PCM candidates | Missing | Extraction produces geometry and text, not classified construction objects. | No recognition of walls, doors, windows, columns or rooms with confidence and a verification queue. | P1 | XL
Authoring | 2D drafting and editing | Partial | cad/editor.tsx with measure, iso views, roundtrip to DXF. | No trim/extend/offset/fillet/array; no hatch or leader tooling. | P2 | L
Authoring | 3D / BIM authoring | Partial | bim/studio.tsx, bim/model.ts, bim/iso.tsx. | No true parametric BIM authoring; no slabs, roofs, stairs, curtain walls. | P2 | XL
Commands | Deterministic command set | Partial | bim/commands.ts, cad/tools.ts; generic ToolRegistry with propose and apply. 108 tests across registry, tools and documentation. | Missing CreateSlab, Beam, Grid, Pipe, Duct, CreateView, CreateSheet, GenerateSchedule. | P1 | L
AI | AI Design Copilot with execution modes | Done | bim/agent2.ts, cad/agent.ts, cad/assistant route; discover-read-resolve-propose-review-apply-audit. | Matches the blueprint execution-mode model closely. The strongest AI surface in the product. | P0 | -
AI | Authored tools (user-defined automation) | Done | bim/authoring.ts, bim_authored_tool table, authoring-panel.tsx; steps are data, never code. | - | P1 | -
Revisions | Revision comparison and impact | Done | cad/compare.ts (content matching, adaptive tolerance) and cad/impact.ts. 39 tests. | - | P0 | -
Documentation | Sheets, tags, dimensions | Partial | bim/sheets.tsx, bim/documentation.ts. 29 tests. | No live schedules as PCM projections, no revision clouds, no sheet sets or issue packages. | P2 | L
Coordination | Clash and clearance detection | Missing | None. | No model federation, no clash workflow. | P2 | XL
Components | Smart components and families | Missing | library_entry table exists for reusable content. | No parametric component definitions with parameters, connectors, constraints or quantity rules. | P2 | L
Takeoff | Drawing-to-quantity measurement | Done | bim/takeoff.ts, cad/measure.ts, drawing_measurement artifact type with source_layers. | - | P0 | -
Validation | Standards and rule validation | Done | standards.ts, validate.ts; standard_violation artifact type; validate and violations endpoints. | - | P1 | -
Desktop | Desktop Studio client | Partial | Electron shell; desktop.ts, desktopBuilds.ts, bundles.ts; signed installers served from /desktop. | No native geometry runtime, no local PCM cache, no GPU renderer, no offline working package. | P2 | XL

## QuantLogix
QuantLogix - 59% complete
Takeoff, quantities and BOQ. 11 features audited: 5 done, 3 partial, 3 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Measurement | Measurement engine | Done | pcm/measure.ts, pcm/units.ts; drawing_measurement artifact type. | - | P0 | -
Measurement | Configurable measurement rules | Missing | Measurement logic is in code, not data. | No measurement_rule table, no versioned rule expressions, no standard references (NRM, POMI, CESMM). | P1 | L
BOQ | BOQ generation from measurements | Done | boq_line artifact type; agent.boq; workflow.quantlogix; surfaces/boq.tsx. | - | P0 | -
BOQ | BOQ export (csv, xlsx) | Done | boq/export.csv and boq/export.xlsx endpoints; xlsx-brand.ts. | - | P1 | -
BOQ | BOQ roster and rate application | Done | boq/roster and boq/rate endpoints; boq/pipeline.tsx. | - | P0 | -
Reconciliation | Multi-source quantity reconciliation | Done | boq/reconcile.ts - modelled vs measured vs manual, 4 verdicts, override trail. 27 tests. | Not yet wired into the BOQ surface, so estimators cannot see disputes. | P1 | S
Traceability | BOQ line to source object trace | Partial | pcm_boq_map, pcm_quantity, artifact_provenance, trace endpoints; source_region now exists and is deployed. | The anchor exists but QuantLogix does not write regions yet - takeoff must record the polygon it measured. | P0 | M
Traceability | Click a quantity, highlight contributing objects | Missing | source_region table deployed 20 Aug; regionsFor() reads the evidence behind any entity. | No longer blocked at the data layer. Needs takeoff to write regions and the editor to highlight them. | P0 | M
Revision | Quantity dirty propagation and remeasure | Partial | pcm_quantity has a status column; cad/impact.ts identifies affected measurements. | Dirty-mark, queue, recompute pipeline is not wired end to end. Stale quantities can be displayed as current. | P1 | M
Revision | BOQ delta between revisions | Partial | cad/compare.ts produces the geometry delta. | No BOQ-level delta report or baseline preservation. | P1 | M
Assemblies | Assemblies and composite items | Missing | None. | - | P2 | M

## CostLogix
CostLogix - 19% complete
Rates, estimating and commercial. 8 features audited: 1 done, 1 partial, 6 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Rates | Rate library | Partial | library_entry table; library endpoints; cost_line artifact type; agent.cost. | No structured rate book with build-ups, regions, currencies or effective dates. | P1 | M
Estimate | Estimate generation and pricing | Done | cost_line artifact type; agent.cost; workflow.costlogix; surfaces/estimate.tsx. | - | P0 | -
Estimate | Estimate scenarios (base, target, BAFO) | Missing | None. | TenderLogix governs revisions and scenarios; none exist. | P1 | M
Commercial | Margin waterfall and markups | Missing | None. | No preliminaries, overhead, escalation, contingency, risk allowance, profit or tax breakdown. | P1 | M
Budget | Budget, commitments, forecast | Missing | None. | Cost control after award is not started. | P2 | XL
EVM | Earned value (PV, EV, AC, SPI, CPI) | Missing | None. | Requires schedule and cost integration. | P2 | XL
Cashflow | Cash flow and S-curves | Missing | None. | - | P2 | L
Change | Variation and change pricing | Missing | None. | No ChangeLogix module exists. | P2 | XL

## ScheduleLogix
ScheduleLogix - 27% complete
Scheduling and project time intelligence. 15 features audited: 4 done, 0 partial, 11 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Engine | Deterministic CPM engine | Done | cpm.ts - forward and backward pass, FS/SS/FF/SF with lag, total float, critical path. | Genuinely deterministic and the AI is kept out of the arithmetic, exactly as the blueprint requires. | P0 | -
Model | Activities and programme storage | Done | project_programme table; schedule_activity artifact type; agent.schedule; workflow.schedulelogix. | - | P0 | -
UI | Gantt and activity grid | Done | programme/gantt.tsx; surfaces/schedule.tsx; programme endpoints. | No frozen columns, bulk edit, saved layouts or network diagram. | P0 | -
Export | Programme export | Done | programme/export.xlsx. | - | P1 | -
Calendars | Global, project and resource calendars | Missing | None. | P0 in the ScheduleLogix matrix (SL-P6-009). CPM without calendars cannot reconcile with P6. | P1 | L
Migration | P6 XER import | Missing | None. | RELEASE-BLOCKING (SL-P6-001). The module's stated mission is migration-first. | P1 | XL
Migration | P6 XML import | Missing | None. | RELEASE-BLOCKING (SL-P6-002). | P1 | XL
Migration | Reconciliation and migration confidence score | Missing | None. | Appendix B requires a signed-off reconciliation package, not an Import Successful message. | P1 | L
Baselines | Baselines and schedule versions | Missing | None. | P0 (SL-P6-023, 024). No baseline compare or immutable published snapshots. | P1 | L
Progress | Progress, data date, percent complete | Missing | None. | P0 (SL-P6-015, 017, 018). | P1 | L
Resources | Resources, roles, histogram, levelling | Missing | None. | P1 tier (SL-P6-025, 033, 034). | P2 | XL
Look-ahead | Look-ahead and work readiness | Missing | None. | Named differentiator; depends on connected procurement and drawing data. | P2 | L
Intelligence | Schedule health scoring | Missing | None. | - | P2 | M
Intelligence | Delay intelligence and recovery scenarios | Missing | None. | Named the key differentiator in section 30. | P2 | XL
Intelligence | What-if sandbox | Missing | None. | - | P2 | L

## ProcureLogix
ProcureLogix - 17% complete
Packages, RFQs and procurement. 6 features audited: 1 done, 0 partial, 5 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Packages | RFQ package grouping by trade and lead time | Done | procurement_package artifact type; agent.procurement; workflow.procurelogix; surfaces/procurement.tsx. | - | P0 | -
RFQ | RFQ issue and vendor management | Missing | None. | No vendor master, no RFQ documents, no issue tracking. | P1 | L
Quotes | Quotation capture and comparison | Missing | None. | No bid levelling or comparison grid. | P1 | L
Coverage | RFQ coverage and gap flags | Missing | None. | Single source, expiry, scope exclusion and missing package flags absent. | P1 | M
Commitments | Purchase orders and commitments | Missing | None. | - | P2 | XL
Delivery | Delivery tracking and long-lead alerts | Missing | None. | - | P2 | L

## NarrativeLogix
NarrativeLogix - 83% complete
Technical narrative and proposal writing. 3 features audited: 2 done, 1 partial, 0 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Drafting | Technical narrative sections | Done | narrative_section artifact type; agent.narrative; workflow.narrativelogix; surfaces/narrative.tsx. | - | P1 | -
Export | Narrative export to markdown | Done | narrative/export.md endpoint. | - | P1 | -
Evidence | Narrative grounded in project evidence | Partial | Sections reference artifacts. | No retrieval layer, so grounding is limited to what is passed in the envelope. | P1 | M

## Platform-Core
Platform / Core - 59% complete
Identity, tenancy, audit, AI governance, operations. 40 features audited: 19 done, 9 partial, 12 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Identity | Authentication | Done | Better Auth; account, session, user, verification tables; rate limit on sign-in. | - | P0 | -
Identity | SSO (SAML / OIDC) | Missing | None. | Enterprise deal blocker. Named in Complete Platform section 15. | P0 | L
Identity | MFA | Missing | Only i18n strings exist; no implementation. | Enterprise deal blocker. | P0 | L
Identity | SCIM provisioning | Missing | None. | - | P1 | M
Tenancy | Multi-tenant isolation | Done | tenant scoping on every query; tenancy.test.ts and tenant-scoping.test.ts (static analysis of every SQL statement). | MySQL has no RLS, so the app layer is the only line. The static-analysis test is the compensating control. | P0 | -
Tenancy | Tenant provisioning and custom domains | Done | tenant_bootstrap, tenant_domain, tenant_invite; provisioning.ts, domains.ts; domain provision endpoints. | - | P0 | -
AuthZ | RBAC roles and permissions | Done | tenant_role, tenant_permission, tenant_role_permission, user_role; iam.ts; 6 seeded roles. | No attribute-based rules (per-package subcontractor access). | P0 | -
Audit | Tamper-evident audit chain | Done | audit_event + audit_chain hash chain; /api/v1/audit and /audit/verify; chain.ts. | - | P0 | -
Provenance | Artifact provenance and review queue | Done | artifact, artifact_type, artifact_provenance with JSON-schema validation; confirm, reject and trace endpoints. | - | P0 | -
Workflow | Workflow and run engine | Done | workflow, workflow_run, workflow_run_step; run_deviation with approve and reject. | - | P0 | -
Jobs | Durable AI job queue | Done | ai_job with idempotency_key; job-queue.ts conditional-UPDATE claims, leases, backoff, reconciler. 21 tests. | - | P0 | -
Jobs | Per-attempt usage ledger | Done | ai_usage_ledger - append-only, one row per attempt, with model alias, prompt version, sensitivity, policy version, cost and outcome. Migration 021. | ai-cost.ts still reads ai_job, so reporting under-counts until it is migrated to the ledger. | P0 | S
AI Gov | Tenant AI policy and data sensitivity | Done | ai/policy.ts + ai_tenant_policy - deployment modes, per-classification boundaries, eligibility before scoring, tenant may narrow never widen. 47 tests. | Not yet consulted by the worker, so nothing enforces it at call time. | P0 | L
AI Gov | Model registry and aliases | Partial | ai/registry.ts + ai_model_registry - aliases, capabilities, rate cards, loud failure on unknown alias. 37 tests with cache. | The four files naming concrete models are not yet migrated to aliases. | P1 | M
AI Gov | Prompt registry with versions | Partial | ai_prompt_version table with prompt_key, version, task_type, prefix hash and approval status. | The worker still reads its prompts from source; nothing populates the table yet. | P1 | M
AI Gov | Budgets (token, cost, latency) | Done | ai/budget.ts - estimate before running, tenant limits, clamping, remedies in the order section 21 recommends. 47 tests with policy. | Not yet wired into dispatch. | P1 | M
AI Gov | Response cache (exact, semantic, artifact) | Partial | ai/cache.ts + ai_response_cache - every answer-changing dimension in the key, scoped invalidation triggers. 37 tests. | Keys and safety rules exist; nothing reads or writes the table yet. | P1 | L
AI Gov | Retrieval / RAG | Partial | retrieval.ts + index-store.ts write and search the chunk table; revision-aware, budget-packed. 34 tests. | Wired for DocLogix only. No embeddings generated, and the AI worker does not call it yet - so agents still answer from the envelope. | P0 | M
Events | Transactional outbox | Done | event_outbox and usage_outbox tables. | No published event catalog or schema versioning. | P0 | -
Observability | Structured logging | Done | log.ts - request ids, AsyncLocalStorage context, key-based redaction. 21 tests. | - | P1 | -
Observability | Metrics, tracing, dashboards | Missing | trace_id exists on ai_job but no OpenTelemetry. | No metrics endpoint, no dashboards, no alerting. | P1 | M
FinOps | AI cost reporting | Partial | ai-cost.ts; /api/v1/ai-cost. 19 tests. | Built on under-counted data until the per-attempt ledger exists. | P0 | S
Entitlements | Modules, plans and entitlements | Done | entitlement_snapshot, entitlements.ts, modules.ts; internal entitlements endpoint. | - | P1 | -
UX | Design system, WCAG 2.2 AA | Done | globals.css semantic tokens with computed contrast; design-system.test.ts (24 tests). | - | P1 | -
UX | Internationalisation EN / AR / FR with RTL | Done | i18n/en, ar, fr; logical CSS properties; technical content not mirrored. | - | P1 | -
UX | Light, dark and system themes | Done | Alias token layer; system bootstrap in layout.tsx. | - | P1 | -
Ops | CI running the test suite | Missing | Six workflow files exist; none has ever executed (PAT lacks workflow scope). | 426 tests and six quality gates run only on a developer machine. | P0 | S
Ops | Automated backup and tested restore | Missing | None. | An untested restore is not a backup. | P0 | M
Ops | Staging environment | Missing | Production only. | Changes are currently validated in production. | P0 | M
Ops | Branch protection and PR review | Missing | autosync commits directly to main. | No review gate on production code. | P0 | S
Ops | schema.sql / migration drift guard | Done | schema-drift.test.ts - fails if a migration creates a table schema.sql does not declare. Found 5 tables drifted since migration 004 whose queries had never been tenant-checked. | - | P0 | -
Ops | Repeatable deploy | Done | deploy.ps1 - sha256-verified resumable upload, migrations, catalog seed gate, worker rebuild. | - | P0 | -
Security | Encryption at rest and key management | Missing | None. | Named in Complete Platform section 15. | P0 | L
Security | Secrets management (Vault / KMS) | Missing | Secrets in .env on the host. | - | P1 | M
Security | Credential rotation | Missing | Outstanding from the earlier security review. | Rotate everything ever committed; confirm the production DB password is not the default. | P0 | S
Security | Upload validation and scan gating | Partial | upload-safety.ts - magic-number vs extension, blocked extensions, macro formats, path traversal, zip-bomb ratio, explicit scan states. 33 tests. | Explicitly not an antivirus. A real scanner still needs to sit behind it, and the upload route does not call this yet. | P1 | M
Security | Port hardening | Partial | 3308, 4000 and 8081 bind to 127.0.0.1 and are externally closed. | 3307 (MySQL), 11434 (Ollama, unauthenticated) and 5000 bind 0.0.0.0; only the provider firewall stops them. | P0 | S
Governance | Architecture Decision Records | Partial | docs/adr - 8 ADRs covering the stack conflict, queue, AI authority, aliases, policy, ledger, cache safety and isolation. | 8 of the ~50 specified. The rest are unwritten, but the ones that settle live contradictions are done. | P1 | M
Integration | Enterprise Integration Hub and connector SDK | Missing | integrations.ts is stub-level. | No connector runtime, canonical mapping or reconciliation engine. | P2 | XL
Knowledge | Cross-module knowledge graph | Partial | pcm_relationship with typed edges, source and confidence. | PCM-scoped only. No Doc-Draw-Quant-Cost-Schedule traversal, no lineage or downstream-impact APIs. | P1 | XL

## ValueLogix
ValueLogix - 0% complete
Value engineering: alternatives, impact, approval, benefit. 16 features audited: 0 done, 0 partial, 16 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Foundation | ValueLogix domain model and VE item | Missing | Specified in PEB 35-ValueLogix (PEB-VAL-001). Nothing in src/ or db/ - no module key, no tables, no artifact type. | The whole module is unbuilt. The specification is unusually complete, so this is implementation work rather than design work. | P2 | XL
Intake | Opportunity detection and value-case intake | Missing | PEB-VAL-010 specifies it. | Where a VE item comes from: a budget overrun, a design change, a procurement signal. | P2 | L
Function | Required function, constraints and success criteria | Missing | PEB-VAL-020 specifies it. | The step that separates value engineering from cost cutting. Without a stated required function, an alternative cannot be judged equivalent. | P2 | M
Baseline | Baseline snapshot with evidence authority and staleness | Missing | PEB-VAL-030 specifies it. | A VE case compares against a baseline; if the baseline moves underneath it the saving is fiction. Depends on the revision and provenance model that already exists. | P2 | M
Alternatives | Option generation and technical equivalence | Missing | PEB-VAL-040 specifies it. | Curtain wall A versus B. Equivalence has to be argued against the stated function, not asserted. | P2 | L
Impact | Cross-domain impact and blast-radius analysis | Missing | PEB-VAL-050 specifies it. cad/impact.ts does the same shape of work for drawings only. | The heart of it: how many drawings, spec sections, BOQ items, activities and packages one substitution touches. Needs the cross-module knowledge graph, which is itself only PCM-scoped today. | P2 | XL
Economics | Cost, lifecycle economics and carbon | Missing | PEB-VAL-060 specifies it. | Capex saving against maintenance, energy and replacement. Needs CostLogix beyond pricing, which is not started. | P2 | L
Delivery | Procurement, constructability and schedule value | Missing | PEB-VAL-070 specifies it. | Lead-time reduction is often worth more than the unit saving. Needs procurement and schedule linkage. | P2 | L
Gates | Compliance, quality, safety and contractual hard gates | Missing | PEB-VAL-080 specifies it. standards.ts validates drawings against rules today. | A saving that breaches a fire rating is not a saving. These are hard gates, not scores. | P2 | M
Scoring | Multi-criteria scoring and scenario comparison | Missing | PEB-VAL-090 specifies it. | Ranking options once the impacts are known. | P2 | M
Approval | Multidisciplinary review and delegated authority | Missing | PEB-VAL-100 specifies it. The artifact review queue and run_deviation approvals are the same shape. | Architect plus structural plus client, with delegation by value and risk. Closest existing analogue in the codebase. | P2 | M
Adoption | Adoption, change control and cross-domain handover | Missing | PEB-VAL-110 specifies it. | An approved option has to flow back into drawing, BOQ, cost and schedule baselines, or the decision is a document nobody acted on. | P2 | L
Realisation | Benefit realisation and reusable value knowledge | Missing | PEB-VAL-120 specifies it. | Did the saving actually land. Feeds the organisational memory the blueprints describe. | P2 | L
AI | AI grounding and authority boundaries | Missing | PEB-VAL-130 specifies it. The propose-review-apply spine and ai/policy.ts already enforce this pattern elsewhere. | AI identifies and explains; the authorised engineer approves. The platform already works this way, so the rule is inherited rather than invented. | P2 | M
Continuous | Value Radar - continuous detection and portfolio analytics | Missing | PEB-VAL-140 specifies it. | VE as a standing capability rather than two workshops. The most differentiating item in the chapter and the furthest from buildable today. | P2 | XL
Certification | Golden workloads and claim certification | Missing | PEB-VAL-150 specifies it. | What has to be true before a ValueLogix claim can be made to a customer. | P2 | L

## Engineering Bible
Engineering Bible - 82% complete
PEB - the 477-document specification the platform is built against. 11 features audited: 8 done, 2 partial, 1 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Governance | Constitution, chapter standard, change management | Done | 00-Governance - 7 documents including PEB-GOV-001 Constitution, GOV-003 Change Management, GOV-006 Specification Quality Gate. | - | P0 | -
Governance | ADR standard and cross-reference standard | Done | PEB-GOV-004 and PEB-GOV-005. | The tenant repo has 8 ADRs written against this standard; the rest of the ~50 named across the blueprints are unwritten. | P1 | M
Coverage | Platform core, architecture and stack | Done | 01-Platform-Core - 42 documents. | - | P0 | -
Coverage | Module chapters for every Logix | Done | DrawingLogix 26, TenderLogix 19, Quantity-BOQ 19, ScheduleLogix 19, DocLogix 19, Cost-Estimate 15, Procurement 18, ChangeLogix 14, FieldLogix 14, ValueLogix 20. | - | P0 | -
Coverage | Cross-cutting: ontology, knowledge graph, geometry, AI platform | Done | 20-Construction-Ontology 11, 21-Knowledge-Graph 11, 22-Geometry-Platform 11, 23-AI-Platform 22. | - | P0 | -
Coverage | Quality, safety, commercial, certification | Done | 30-Quality 17, 31-Safety 19, 32-Commercial-Finance 14, 33-Release-Certification 14. | - | P0 | -
Automation | Docs validation workflow | Done | .github/workflows/docs-validation.yml. | - | P1 | -
Automation | Publish workflow | Done | .github/workflows/publish-docs.yml. | - | P2 | -
Sync | PEB synchronisation gate on the code repos | Partial | peb-sync.yml added by the open PR on both preckon-tenant and preckon-host; PEB Synchronization passes on both. | Still in an unmerged draft PR. Until those merge, nothing enforces that a code change references the specification it implements. | P0 | S
Traceability | Code traceable to the chapter it implements | Missing | No PEB reference appears in tenant source or commit messages. | The Bible specifies the platform in 477 documents and the code cites none of them. A reader cannot get from a module to its specification, or tell which chapters are implemented. | P1 | L
Currency | Specification matches what is built | Partial | Chapters exist for modules that are 17-27% built (ProcureLogix, ScheduleLogix, CostLogix) and for one that is 0% (ValueLogix). | The Bible describes the intended platform, not the current one. That is legitimate for a specification, but nothing records which chapters are implemented, so it cannot answer what is left. | P1 | M

## P0 Backlog
Everything marked P0, across all modules
These block enterprise readiness or are actively wrong today. Sorted by module.
Module | Feature | Status | Why it blocks | Effort | Priority
TenderLogix | Requirements extraction with clause citation | Partial | Clauses are extracted but are not turned into tracked Requirement objects with owner, due date, response and status. | L | P0
TenderLogix | Compliance matrix | Partial | No matrix view, no mandatory flag, no Requirement-Evidence-Response-Approval chain. | L | P0
DocLogix | Screens for register, review, transmittals and search | Missing | Everything built today is reachable only through the API. This is the honest limit on calling the module done. | L | P0
QuantLogix | BOQ line to source object trace | Partial | The anchor exists but QuantLogix does not write regions yet - takeoff must record the polygon it measured. | M | P0
QuantLogix | Click a quantity, highlight contributing objects | Missing | No longer blocked at the data layer. Needs takeoff to write regions and the editor to highlight them. | M | P0
Platform / Core | SSO (SAML / OIDC) | Missing | Enterprise deal blocker. Named in Complete Platform section 15. | L | P0
Platform / Core | MFA | Missing | Enterprise deal blocker. | L | P0
Platform / Core | Retrieval / RAG | Partial | Wired for DocLogix only. No embeddings generated, and the AI worker does not call it yet - so agents still answer from the envelope. | M | P0
Platform / Core | AI cost reporting | Partial | Built on under-counted data until the per-attempt ledger exists. | S | P0
Platform / Core | CI running the test suite | Missing | 426 tests and six quality gates run only on a developer machine. | S | P0
Platform / Core | Automated backup and tested restore | Missing | An untested restore is not a backup. | M | P0
Platform / Core | Staging environment | Missing | Changes are currently validated in production. | M | P0
Platform / Core | Branch protection and PR review | Missing | No review gate on production code. | S | P0
Platform / Core | Encryption at rest and key management | Missing | Named in Complete Platform section 15. | L | P0
Platform / Core | Credential rotation | Missing | Rotate everything ever committed; confirm the production DB password is not the default. | S | P0
Platform / Core | Port hardening | Partial | 3307 (MySQL), 11434 (Ollama, unauthenticated) and 5000 bind 0.0.0.0; only the provider firewall stops them. | S | P0
Engineering Bible | PEB synchronisation gate on the code repos | Partial | Still in an unmerged draft PR. Until those merge, nothing enforces that a code change references the specification it implements. | S | P0

## Evidence
What exists - counted, not assumed
Queried from the repository and the deployed production database.
Area | Count | Detail
Modules seeded | 8 | tenderlogix, drawlogix, doclogix, quantlogix, costlogix, schedulelogix, narrativelogix, procurelogix
Artifact types | 18 | bid_approval, bid_decision, boq_line, client_query, compliance_item, cost_line, document, drawing_index, drawing_measurement, narrative_section, procurement_package, proposal_doc, rfi, risk, schedule_activity, spec_clause, standard_violation, tender_summary
AI agents | 20 | approval_prep, bid_qualification, boq, clarification, commercial, compliance, compliance_lead, construction_copilot, cost, document, drawing, knowledge, narrative, procurement, proposal, rfi, risk, schedule, specification, tender
Workflows | 14 | One per module plus 6 TenderLogix sub-workflows
Database tables | 86 | Was 56 on 19 Aug. DocLogix added 12: register, revisions, transmittal x3, source_region, numbering_scheme, distribution x2, review x2, comments
Migrations | 29 | 019 and 020 are DocLogix; both validated against MySQL 8 in a scratch database, 020 re-run to prove idempotency
API routes | 87 | Was 78. Seven new DocLogix endpoints plus search
Module surfaces | 10 | boq, drawings, estimate, narrative, procurement, schedule, specs, tender, common, generic - none yet for the DocLogix register
Tests | 1476 passing | Unit and governance, green in CI on ubuntu with a real MySQL service. vitest was upgraded 2.1.8 -> 4.1.11 to clear a critical advisory rather than filter it.
Deterministic engines | 15 | cpm, pcm/measure, boq/reconcile, cad/compare, cad/impact, standards, validate, doc/numbering, doc/revision, doc/compare, doc/retrieval, ai/policy, ai/budget, ai/cache, upload-safety
Live sheets in production | 31 | Average 8.1 MB, largest 37 MB - still the biggest user-facing performance issue
Deployed versions | next 15.5.23 | postcss 8.5.26 - verified inside the running container
CI runs | green | Tenant CI now runs typecheck, schema+migrations, seed, 1476 unit tests, migration re-runnability, production build, npm audit and credential hygiene, plus a 28-spec Playwright job. PEB Synchronization passes on both repos.
Engineering Bible | 477 files | techsmeinc/preckon-engineering-bible - 28 numbered chapters with governance, quality gates and its own docs-validation CI. This is the PRA the Master Blueprint names as the detailed source of truth.
PEB ValueLogix chapter | 20 docs | PEB-VAL-001 to 150 plus a blueprint and a competitive parity matrix. Covers required function, alternatives, blast radius, lifecycle economics, hard gates, delegated approval, benefit realisation, AI authority boundaries and continuous detection.
Org repositories | 10 | preckon-tenant, preckon-host, preckon-engineering-bible, preckon-product-specs, preckon-system, construction-intelligence, tenderlogix (x3), clavis
Open pull requests | 2 | preckon-host #1 is green on all four checks. preckon-tenant #1 went from 6 failing specs to 1 across three fixes: DEMO_STUB_MODE for the keyless CI worker, a GET issued at a POST-only export, and a hard-coded project uuid.
PEB implementation waves | 10 tracks / 88 epics | 34-Implementation-Program/ENGINEERING-BACKLOG-WAVES.md: Waves 0-6 plus parallel Enterprise Integration and AI Fabric, plus release certification. Each epic names its PEB owner and the exit evidence required.
PEB Wave-0 gap inventory | 37 KB | WAVE-0-CODE-TO-PEB-GAP-INVENTORY.md already maps existing code to canonical contracts - the document this workbook duplicates from the code side.
ADRs | 8 | Of ~50 specified. Cover the three-way stack conflict, queue choice, AI authority, model aliases, tenant policy, usage ledger, cache safety and tenant isolation.

## PEB Waves
PEB implementation waves - where we actually are
Epics from 34-Implementation-Program/ENGINEERING-BACKLOG-WAVES.md, scored against the tenant codebase. An epic counts as Done only where the exit evidence the PEB names could be produced today.
Wave | Epic | Outcome | PEB pri | Our status | Where it stands
Wave 0 - Runway | IMP-W0-01 | Current code to PEB inventory | P0 | Partial | WAVE-0-CODE-TO-PEB-GAP-INVENTORY.md exists in the PEB (37 KB). No code cites a PEB id, so the mapping is one-directional.
Wave 0 - Runway | IMP-W0-02 | Reproducible dev/test environment | P0 | Partial | docker compose brings up db/app/worker/cad. But the local DB drifted behind the code (due_date, lease_until missing) and .env corruption stopped compose parsing entirely - a fresh-environment smoke test would have caught both.
Wave 0 - Runway | IMP-W0-03 | DB migration and contract versioning | P0 | Partial | 29 migrations, re-runnability proven in CI. schema-drift.test.ts now guards tables AND columns. No rollback path and no contract versioning.
Wave 0 - Runway | IMP-W0-04 | CI quality baseline | P0 | Partial | typecheck, 1476 unit tests, build, npm audit, credential hygiene, PEB sync, 28 e2e. No a11y or contract checks.
Wave 0 - Runway | IMP-W0-05 | Golden project fixture framework | P0 | Partial | seed-aigcc.mjs builds one workspace. It is not versioned, and until this week it reported 'timeout' while silently exiting 0 over a half-seeded database.
Wave 0 - Runway | IMP-W0-06 | Observability baseline | P0 | Partial | Structured request logs with request ids and an audit chain. No metrics, no cross-service trace. The reconciler was failing every pass locally and nothing surfaced it.
Wave 1 - Platform spine | IMP-W1-01 | Tenant/org/user identity | P0 | Done | Host and tenant planes, tenant_id on every scoped table, tenant-scoping.test.ts proves isolation.
Wave 1 - Platform spine | IMP-W1-02 | Roles/auth/authz/sessions | P0 | Done | Better Auth, server-side requirePermission, role keys, 2FA column, SCIM external id.
Wave 1 - Platform spine | IMP-W1-03 | Project core and settings | P0 | Partial | Projects, lifecycle, currency. Calendars, regions and units are not modelled - which is also what blocks CPM calendars in W3-07.
Wave 1 - Platform spine | IMP-W1-04 | Evidence/object storage spine | P0 | Done | Uploads, document revisions, supersession, artifact_provenance, source_region.
Wave 1 - Platform spine | IMP-W1-05 | Durable jobs / event outbox | P0 | Done | MySQL-backed queue with conditional-UPDATE claims, leases, a reconciler and event_outbox. No broker.
Wave 1 - Platform spine | IMP-W1-06 | Shared error/idempotency/audit contracts | P0 | Partial | Uniform error envelope and a tamper-evident audit chain. Idempotency is per-endpoint rather than a contract.
Wave 1 - Platform spine | IMP-W1-07 | Design system runtime | P0 | Partial | Shared surfaces, tokens and components exist. No Storybook and no visual regression.
Wave 1 - Platform spine | IMP-W1-08 | Accessibility / RTL / i18n / theme | P0 | Partial | EN/AR/FR with RTL, proven by 5 passing e2e specs. No automated contrast or keyboard fixtures, so the a11y half is unevidenced.
Wave 1 - Platform spine | IMP-W1-09 | Application state / conflict UX | P0 | Partial | StageEmpty, skeletons and error surfaces. No conflict UX and no state gallery.
Wave 2 - Precon slice | IMP-W2-01 | Tender package / opportunity lifecycle | P0 | Partial | Projects carry a bid_pursuit lifecycle. Tender package identity is not a first-class object.
Wave 2 - Precon slice | IMP-W2-02 | Tender document / addendum intake | P0 | Done | DocLogix at 80%: register, revisions, supersession, transmittals, retention.
Wave 2 - Precon slice | IMP-W2-03 | Requirements / compliance proposals | P0 | Partial | spec_clause extraction with provenance. Clauses are not tracked requirement objects - the gap that also blocks VAL-020.
Wave 2 - Precon slice | IMP-W2-04 | Scope / responsibility breakdown | P0 | Missing | No work-package scope model and no gap surfacing.
Wave 2 - Precon slice | IMP-W2-05 | Draw source intake / revision context | P0 | Partial | PDF and DXF/DWG intake through the cad sidecar, with a vision pre-pass. No IFC or Revit.
Wave 2 - Precon slice | IMP-W2-06 | Quantity measurement context / rules | P0 | Partial | Rule packs and units exist. Precision and rounding contracts are not pinned.
Wave 2 - Precon slice | IMP-W2-07 | Deterministic quantity kernel | P0 | Partial | Deterministic count/length/area. No cross-runtime golden corpus, so reproducibility is asserted rather than proven.
Wave 2 - Precon slice | IMP-W2-08 | BOQ versioning / reconciliation | P0 | Done | boq/reconcile.ts compares employer/manual/Preckon bills and refuses to present a disputed quantity as agreed.
Wave 2 - Precon slice | IMP-W2-09 | QS review / overrides / takeoff workbench | P0 | Partial | Review queue and confirm/reject. Overrides do not carry staleness.
Wave 2 - Precon slice | IMP-W2-10 | Cost rate / estimate buildup core | P0 | Partial | Rate book and priced lines. No versioned estimate over a QTY snapshot - CostLogix is 19%.
Wave 2 - Precon slice | IMP-W2-11 | Tender commercial / estimate integration | P0 | Missing | No snapshot pinning, so a tender cannot consume an exact cost version.
Wave 2 - Precon slice | IMP-W2-12 | Tender readiness gate | P0 | Missing | No fail-closed blocker model. This is the '99% score with one blocker' test the PEB names.
Wave 2 - Precon slice | IMP-W2-13 | AI tender/document assistance | P0 | Done | Grounded retrieval with citations, typed tools, propose-review-apply, ai/policy.ts authority limits.
Wave 2 - Precon slice | IMP-W2-14 | Preconstruction E2E golden scenario | P0 | Partial | The golden-path e2e walks the chain, but on stub agents; it asserts shape, not quantity truth.
Wave 3 - Draw + Schedule | IMP-W3-01 | PCM / construction object model | P0 | Partial | 13 PCM tables and a parametric model. Constraint and identity tests are thin.
Wave 3 - Draw + Schedule | IMP-W3-02 | Atomic changesets / undo / concurrency | P0 | Partial | bim_proposal gives preview/commit. No undo stack and no concurrency conflict handling.
Wave 3 - Draw + Schedule | IMP-W3-03 | Studio workspace / local cache | P0 | Partial | The Electron desktop shell exists with its own renderer. No offline cache or reconnect story.
Wave 3 - Draw + Schedule | IMP-W3-04 | Web review / progressive authoring | P0 | Partial | BIM Studio authors in the browser through the tool registry. No capability matrix between surfaces.
Wave 3 - Draw + Schedule | IMP-W3-05 | Drawing QA / coordination | P1 | Partial | standards.ts validates drawings against rule sets. No clash or constructability checks.
Wave 3 - Draw + Schedule | IMP-W3-06 | Design to quantity traceability | P0 | Partial | cad/impact.ts traces drawings to measurements. Revision invalidation is not wired end to end.
Wave 3 - Draw + Schedule | IMP-W3-07 | Schedule identity / WBS / calendar | P0 | Partial | WBS and activities exist. No calendars - so no working-day arithmetic.
Wave 3 - Draw + Schedule | IMP-W3-08 | Deterministic CPM | P0 | Done | A real CPM pass with float and critical path, exercised by 10 programme e2e tests.
Wave 3 - Draw + Schedule | IMP-W3-09 | Baseline / progress governance | P0 | Missing | No data date, no baselines, no publication authority. This is most of why ScheduleLogix scores 27%.
Wave 3 - Draw + Schedule | IMP-W3-10 | P6 XER/XML migration | P0 | Missing | No importer. Named as P0 because enterprise planners will not retype a programme.
Wave 3 - Draw + Schedule | IMP-W3-11 | Planner workspace | P0 | Partial | Gantt with grid, zoom, filters, CSV and XLSX export. Not tested at enterprise scale.
Wave 3 - Draw + Schedule | IMP-W3-12 | Connected design/schedule scenario | P0 | Missing | No cross-domain handoff from design or quantity into schedule.
Wave 4 - Procure/Change/Controls | IMP-W4-01 | Procurement planning / packages | P1 | Partial | Package grouping exists. No requisitions or strategy.
Wave 4 - Procure/Change/Controls | IMP-W4-02 | Supplier / RFQ / bid evaluation | P1 | Missing | No supplier identity, RFQ or normalisation. ProcureLogix is 17%.
Wave 4 - Procure/Change/Controls | IMP-W4-03 | Award / commitment / delivery | P1 | Missing | No commitments - which is also why VE cannot price a lead time.
Wave 4 - Procure/Change/Controls | IMP-W4-04 | Change intake / evidence | P1 | Missing | ChangeLogix has 14 PEB chapters and no implementation.
Wave 4 - Procure/Change/Controls | IMP-W4-05 | Quantity/cost/schedule impact | P1 | Missing | The same blast-radius traversal ValueLogix needs. Nothing beyond drawings to measurements.
Wave 4 - Procure/Change/Controls | IMP-W4-06 | Change approval / activation | P1 | Missing | The approval spine exists generically (run_deviation, review queue) but no change domain.
Wave 4 - Procure/Change/Controls | IMP-W4-07 | Controls period / baseline / KPI | P1 | Missing | No control snapshots.
Wave 4 - Procure/Change/Controls | IMP-W4-08 | Variance / risk / decision reporting | P1 | Missing | No projection layer.
Wave 5 - Field/Quality/Safety | IMP-W5-01 | Field daily / workforce / equipment | P1 | Missing | FieldLogix: 14 PEB chapters, no code.
Wave 5 - Field/Quality/Safety | IMP-W5-02 | Installed quantity / progress evidence | P1 | Missing | No actuals capture.
Wave 5 - Field/Quality/Safety | IMP-W5-03 | Offline mobile sync | P1 | Missing | No mobile client.
Wave 5 - Field/Quality/Safety | IMP-W5-04 | Quality ITP / inspection / test | P1 | Missing | Quality: 17 PEB chapters, no code.
Wave 5 - Field/Quality/Safety | IMP-W5-05 | NCR / CAPA / punch | P1 | Missing | Not started.
Wave 5 - Field/Quality/Safety | IMP-W5-06 | Safety planning / PTW / JSA | P1 | Missing | Safety: 19 PEB chapters, no code.
Wave 5 - Field/Quality/Safety | IMP-W5-07 | Safety observation / incident | P1 | Missing | Not started.
Wave 5 - Field/Quality/Safety | IMP-W5-08 | Workface readiness | P1 | Missing | Depends on five domains that do not exist yet.
Wave 6 - Commercial | IMP-W6-01 | Contract / value baseline | P1 | Missing | Commercial-Finance: 14 PEB chapters, no code.
Wave 6 - Commercial | IMP-W6-02 | Valuation / payment applications | P1 | Missing | Not started.
Wave 6 - Commercial | IMP-W6-03 | Retention / deductions / securities | P1 | Missing | Not started.
Wave 6 - Commercial | IMP-W6-04 | Supplier / subcontract payables | P1 | Missing | Depends on Wave 4 commitments.
Wave 6 - Commercial | IMP-W6-05 | Claims / receivables / cash | P2 | Missing | Not started.
Wave 6 - Commercial | IMP-W6-06 | Margin / exposure / AI assistance | P2 | Missing | Not started.
Wave 6 - Commercial | IMP-W6-07 | Handover / completion profile | P1 | Missing | Not started.
Parallel E - Integration | IMP-E-01 | Connector SDK / runtime | P0 | Missing | Enterprise-Integration: 19 PEB chapters, no connector runtime.
Parallel E - Integration | IMP-E-02 | Connectivity / secrets / private network | P0 | Partial | Service tokens and a worker with no DB handle. No secret broker or private networking.
Parallel E - Integration | IMP-E-03 | Canonical envelope / identity / mapping | P0 | Missing | No vendor-neutral envelope.
Parallel E - Integration | IMP-E-04 | Sync / replay / SoR / reconciliation | P0 | Missing | Not started.
Parallel E - Integration | IMP-E-05 | Mapping studio / shadow onboarding | P1 | Missing | Not started.
Parallel E - Integration | IMP-E-06 | Edge agent | P1 | Missing | Not started.
Parallel E - Integration | IMP-E-07 | Demand-backed connector #1 | P1 | Missing | Not started.
Parallel E - Integration | IMP-E-08 | Demand-backed connector #2 | P1 | Missing | Not started.
Parallel E - Integration | IMP-E-09 | Governed write-back | P2 | Missing | Correctly last - write-back before reconciliation maturity is how integrations corrupt a system of record.
Parallel A - AI Fabric | IMP-AI-01 | Request router / model registry | P0 | Partial | ai/registry.ts and model ids are env-overridable. Routing is not policy-driven.
Parallel A - AI Fabric | IMP-AI-02 | Context / project memory | P0 | Done | doc/retrieval.ts: meaning-based chunking, hybrid ranking, budget packing, and it refuses to answer from a superseded revision.
Parallel A - AI Fabric | IMP-AI-03 | Exact / semantic / tool cache | P0 | Partial | ai/cache.ts exists. Invalidation is not proven by a golden suite.
Parallel A - AI Fabric | IMP-AI-04 | Typed tool runtime | P0 | Done | ToolRegistry with typed params, alias resolution and coercion, shared by BIM Studio and the CAD editor. The model proposes; a person applies.
Parallel A - AI Fabric | IMP-AI-05 | AI eval harness | P0 | Missing | No golden workloads, so no quality gate on a model or route change.
Parallel A - AI Fabric | IMP-AI-06 | FinOps / usage attribution | P0 | Partial | ai_usage_ledger and ai/budget.ts record spend. No reconciliation test.
Parallel A - AI Fabric | IMP-AI-07 | Private model serving | P1 | Missing | Anthropic only.
Parallel A - AI Fabric | IMP-AI-08 | Sovereign / VPC / on-prem profile | P1 | Missing | No egress-disabled profile.
Release certification | IMP-REL-01 | Release profile / capability matrix | P0 | Missing | Nothing states what this build may claim.
Release certification | IMP-REL-02 | Evidence manifest / lineage | P0 | Missing | Provenance exists per artifact; there is no release-level evidence export.
Release certification | IMP-REL-03 | Golden project runner | P0 | Partial | 28 e2e specs over one seeded workspace. Not a cross-domain runner.
Release certification | IMP-REL-04 | Security / UX gate automation | P0 | Partial | Tenant isolation, trust boundary and credential hygiene run in CI. No a11y, RTL or theme gates.
Release certification | IMP-REL-05 | Performance / recovery harness | P1 | Missing | No capacity band, no restore drill.
Release certification | IMP-REL-06 | Migration / portability harness | P1 | Missing | No semantic import/export.
Release certification | IMP-REL-07 | Readiness / rollout / claims | P0 | Missing | No pilot-to-GA gate.

## Wave Rollup
Completion by wave
The same epics, aggregated. Waves 4-6 and the parallel tracks are where the product is not yet a product.
Wave | Epics | Done | Partial | Missing | Complete
Wave 0 - Runway | 6 | 0 | 6 | 0 | 50
Wave 1 - Platform spine | 9 | 4 | 5 | 0 | 72
Wave 2 - Precon slice | 14 | 3 | 8 | 3 | 50
Wave 3 - Draw + Schedule | 12 | 1 | 8 | 3 | 42
Wave 4 - Procure/Change/Controls | 8 | 0 | 1 | 7 | 6
Wave 5 - Field/Quality/Safety | 8 | 0 | 0 | 8 | 0
Wave 6 - Commercial | 7 | 0 | 0 | 7 | 0
Parallel E - Integration | 9 | 0 | 1 | 8 | 6
Parallel A - AI Fabric | 8 | 2 | 3 | 3 | 44
Release certification | 7 | 0 | 2 | 5 | 14

## ValueLogix Plan
ValueLogix - the PR sequence the PEB already prescribes
From 34-Implementation-Program/VALUELOGIX-IMPLEMENTATION-PLAN.md. Every step is unbuilt; the point of this sheet is the ORDER and what blocks each one. The specification is not the gap.
Step | Deliverable | PEB | Status | What it needs first
V-00 | Domain scaffold and migrations | VAL-001, VAL-150 | Missing | Tables, tenant/project scoping, state machines, audit integration, API skeleton with no fake success responses. Nothing blocks this - it is the one step that could start today.
V-01 | Opportunity + function/constraint + baseline | VAL-010, 020, 030 | Missing | Needs requirements as tracked objects (W2-03). Acceptance explicitly includes: an AI or radar signal cannot claim savings.
V-02 | Alternatives + impact orchestration | VAL-040, 050 | Missing | The blast-radius traversal. Blocked on the cross-module knowledge graph - cad/impact.ts covers drawings to measurements only.
V-03 | Economics + procurement/schedule value | VAL-060, 070 | Missing | Blocked on CostLogix (19%), ProcureLogix (17%) and ScheduleLogix baselines (missing). Lifecycle cost and lead time have nowhere to come from.
V-04 | Hard gates + scoring + review/decision | VAL-080, 090, 100 | Missing | The closest to buildable after V-00: standards.ts already validates against rules, and the review queue plus run_deviation approvals are the same shape as delegated authority.
V-05 | Adoption + realization | VAL-110, 120 | Missing | Needs somewhere to hand an approved option back to - drawing, BOQ, cost and schedule baselines.
V-06 | AI assistance | VAL-130 | Missing | Least new work conceptually: propose-review-apply and ai/policy.ts already enforce that AI explains and a person approves. Inherited, not invented.
V-07 | Value Radar | VAL-140 | Missing | Continuous detection and portfolio analytics. The most differentiating item and the furthest from buildable.
V-08 | Golden certification | VAL-150 | Missing | What has to be true before a ValueLogix claim can be made to a customer.
First MVP - IN | material substitution, human-created design alternative, standardization, exact baseline, QTY/Cost/Procurement/Schedule impacts, hard gates, score/review, adoption tracking, realization, initial Radar, AI proposals
First MVP - explicitly NOT in | autonomous generative building redesign, automatic structural/code approval, supplier marketplace award, automatic contract variation, black-box 'AI value score', or guaranteed-savings claims
Definition of done | current evidence -> function -> immutable baseline -> alternatives -> authoritative impacts -> blockers -> multidisciplinary decision -> controlled adoption -> actual realized benefit
ValueLogix v1 is not done because a VE form exists.