## Contents
Preckon — platform report and test plan
Live system as at 27 August 2026. Prepared 28 August 2026.
PART 1 | What the system shows today
Executive summary | The story in one page, and what we are asking for | Report
Stage by stage | How each step of the bid performed, with timing | Report
Tokens & cost by step | Tokens in, out and cost for all 17 steps | Report
Tokens & cost by project | The same, charged to each of the six projects | Report
Where work is stuck | The approval queue — 1,367 items waiting | Report
Cost scaling | Editable scenarios for what a year would cost | Report
Issues & actions | Seven items, prioritised, with owner and date to fill in | Report
PART 2 | The plan to test it properly
Test progress | Rolls up from the five test sheets as they are filled in | Test
Test · Functional | 40 cases across all modules and the platform | Test
Test · Documents | 15 runs — processing time and tokens by file size | Test
Test · Drawings | 12 runs — simple, medium, complex and scanned | Test
Test · Tokens | All 17 steps, and the total for one full bid | Test
Test · Accuracy | 10 extraction types, with precision and recall | Test
PART 3 | Reference
Targets | Every threshold, with today's figure beside it | Reference
Test data needed | The files to prepare before testing can start | Reference
Glossary | Plain definitions for every term used | Reference
Colour key
Cream | You fill this in.
Grey | Calculates itself — do not type over it.
Red | Needs a decision or is not working.
Amber | Works, but worth watching.
Green | Working.

## Executive summary
The numbers
Jobs run | 228 | Across six projects.
AI requests | 88 | Across 14 active steps.
Blocked by privacy rule | 44 | Refused before reaching the AI. Cost nothing.
Total tokens | 26040 | See the caveat below.
Total cost | 3.36 | Arithmetic on a placeholder. Not spend.
Waiting for approval | 1367 | This is where work is stopping.
Actually approved | 8 | Out of 1,367. None rejected either.
Repeat work reused | 0 | The reuse feature is switched off.
System errors | 2 | In pricing and procurement.
Before the cost figure is used for anything
Every successful request records the same fixed usage — 250 tokens in, 60 out — no matter what it was given. A 0.2 MB document and a 33 MB document both record 310 tokens. The breakdown by step and project is shaped correctly, but the absolute dollars are not real spend.
What we are asking for
• A decision on the data-classification policy, so ordinary tender documents can be processed by the AI.
• An owner for the approval queue — 1,367 items are waiting on a person.
• Sign-off on the test plan in Part 2, and the targets that go with it.

## Stage by stage
‹ Contents
# | Step | What it does | Requests | Blocked | Errors | Typical time | Queue wait | Status | What to read into it
1 | Reading documents | Sorts and splits the uploaded tender pack | 30 | 15 | 0 | 4 sec | — | Working
2 | Tender reading | Pulls summary, dates and requirements | 6 | 3 | 0 | 4 min | 5 hrs | Action | Waits far longer than it takes to run.
3 | Bid / no-bid decision | Recommends whether to pursue | 2 | 1 | 0 | 6 min | — | Action | Slow enough that a person would notice.
4 | Specification reading | Extracts clauses from the specification | 2 | 1 | 0 | 2 sec | — | Working
5 | Drawing indexing | Catalogues each drawing sheet | 0 | 0 | 0 | — | — | Blocked | Never ran. Nothing produced at all.
6 | Drawing take-off | Measures quantities off the drawings | 0 | 0 | 0 | — | — | Blocked | Never ran. Nothing produced at all.
7 | Bill of quantities | Turns measurements into bill lines | 6 | 3 | 0 | 2 min | — | Working
8 | Pricing | Applies rates to the bill lines | 4 | 2 | 1 | 5 min | 4 hrs | Action | Waits far longer than it takes to run.
9 | Compliance checks | Checks the bid against requirements | 6 | 3 | 0 | 2 sec | 5 hrs | Action | Waits far longer than it takes to run.
10 | Risk assessment | Flags risks on the bid | 4 | 2 | 0 | 10 sec | — | Working
11 | Programme / schedule | Builds the works programme | 2 | 1 | 0 | 16 sec | 37 hrs | Action | Waits far longer than it takes to run.
12 | Procurement packages | Groups bill lines into packages | 2 | 1 | 1 | 8 sec | 26 hrs | Action | Waits far longer than it takes to run.
13 | Technical narrative | Writes the technical submission | 0 | 0 | 0 | — | — | Blocked | Never ran. Nothing produced at all.
14 | Proposal writing | Drafts the proposal document | 6 | 3 | 0 | 1 sec | — | Working
15 | Bid approval pack | Assembles the approval pack | 6 | 3 | 0 | 2 sec | — | Working
16 | Client clarifications | Drafts questions back to the client | 2 | 1 | 0 | 10 sec | — | Working
17 | Copilot answers | Answers questions people ask | 10 | 5 | 0 | 4 sec | — | Working

## Tokens & cost by step
‹ Contents
# | Step | Requests | Blocked | Errors | Tokens in | Tokens out | Total tokens | Cost | Cost / request | % of cost | Running cost
1 | Reading documents | 30 | 15 | 0 | 7500 | 1800 | 9300 | 1.2 | 0.04 | 35.71% | 1.2
2 | Tender reading | 6 | 3 | 0 | 1500 | 360 | 1860 | 0.24 | 0.04 | 7.143% | 1.44
3 | Bid / no-bid decision | 2 | 1 | 0 | 500 | 120 | 620 | 0.08 | 0.04 | 2.381% | 1.52
4 | Specification reading | 2 | 1 | 0 | 500 | 120 | 620 | 0.08 | 0.04 | 2.381% | 1.6
5 | Drawing indexing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1.6
6 | Drawing take-off | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1.6
7 | Bill of quantities | 6 | 3 | 0 | 1500 | 360 | 1860 | 0.24 | 0.04 | 7.143% | 1.84
8 | Pricing | 4 | 2 | 1 | 500 | 120 | 620 | 0.08 | 0.02 | 2.381% | 1.92
9 | Compliance checks | 6 | 3 | 0 | 1500 | 360 | 1860 | 0.24 | 0.04 | 7.143% | 2.16
10 | Risk assessment | 4 | 2 | 0 | 1000 | 240 | 1240 | 0.16 | 0.04 | 4.762% | 2.32
11 | Programme / schedule | 2 | 1 | 0 | 500 | 120 | 620 | 0.08 | 0.04 | 2.381% | 2.4
12 | Procurement packages | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 2.4
13 | Technical narrative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2.4
14 | Proposal writing | 6 | 3 | 0 | 1500 | 360 | 1860 | 0.24 | 0.04 | 7.143% | 2.64
15 | Bid approval pack | 6 | 3 | 0 | 1500 | 360 | 1860 | 0.24 | 0.04 | 7.143% | 2.88
16 | Client clarifications | 2 | 1 | 0 | 500 | 120 | 620 | 0.08 | 0.04 | 2.381% | 2.96
17 | Copilot answers | 10 | 5 | 0 | 2500 | 600 | 3100 | 0.4 | 0.04 | 11.9% | 3.36
| TOTAL | 88 | 44 | 2 | 21000 | 5040 | 26040 | 3.36 | 0.038182 | 100% | 3.36
Reading documents is 36% of all cost on its own — it runs once per uploaded file, so it scales with the size of the tender pack rather than the number of bids. Blocked requests cost nothing, so the true cost per completed request is roughly double the column shown. Blended rate: $0.1290 per 1,000 tokens.

## Tokens & cost by project
‹ Contents
Tokens and cost — by project
Every request charged to the project that raised it.
Project | Requests | Tokens in | Tokens out | Total tokens | Cost | Cost / request | % of cost | Errors | Note
DV Quaters | 22 | 5500 | 1320 | 6820 | 0.88 | 0.04 | 26.19% | 0
DV Quaters Demo | 20 | 5000 | 1200 | 6200 | 0.8 | 0.04 | 23.81% | 0
venkat1 | 18 | 4500 | 1080 | 5580 | 0.72 | 0.04 | 21.43% | 0
Sowbelly Gulch Project | 18 | 3500 | 840 | 4340 | 0.56 | 0.031111 | 16.67% | 2 | Both system errors here — and it carries the real drawings.
venkat02 | 8 | 2000 | 480 | 2480 | 0.32 | 0.04 | 9.524% | 0
Shruthi2 | 2 | 500 | 120 | 620 | 0.08 | 0.04 | 2.381% | 0
TOTAL | 88 | 21000 | 5040 | 26040 | 3.36 | 0.038182 | 100% | 2
Four of the six are test or demo projects. Cost per request is almost identical across all six — another way of seeing that usage is recorded as a fixed number rather than measured.

## Where work is stuck
‹ Contents
Where work is stuck
What is waiting | Waiting | Approved | Approved % | Note
Bill of quantity lines | 796 | 1 | 0.1256% | Biggest queue in the system.
Priced lines | 254 | 0 | 0% | Nothing decided either way.
Drawing measurements | 76 | 0 | 0% | Nothing decided either way.
Specification clauses | 65 | 0 | 0% | Nothing decided either way.
Programme activities | 63 | 0 | 0% | Nothing decided either way.
Risks | 44 | 0 | 0% | Nothing decided either way.
Procurement packages | 18 | 1 | 5.556%
Compliance items | 12 | 0 | 0% | Nothing decided either way.
Tender summaries | 11 | 0 | 0% | Nothing decided either way.
Drawing indexes | 10 | 0 | 0% | Nothing decided either way.
Proposal documents | 6 | 3 | 50% | Being worked.
Bid approvals | 6 | 3 | 50% | Being worked.
Bid decisions | 3 | 0 | 0% | Nothing decided either way.
Client queries | 3 | 0 | 0% | Nothing decided either way.
TOTAL | 1367 | 8 | 0.5852%
Why this matters more than anything else here
Everything upstream is producing work. Nothing downstream is moving. That nothing has been rejected either suggests an unworked queue rather than people refusing the output — worth confirming before it is read as a quality signal.

## Cost scaling
‹ Contents
What this scales to
Straight arithmetic. Change the cream cells and the rest follows.
Assumptions — edit these
Cost per project, as measured | 0.56
Projects per year | 40
Uplift once usage is measured | 10 | x
Result
Scenario | Per project |  | Per year | What it assumes
As measured today | 0.56 |  | 22.4 | The placeholder usage figure, unchanged.
With usage measured properly | 5.6 |  | 224 | Assumes real documents use the uplift above. A guess until the counter is fixed.
If blocked requests also ran | 11.2 |  | 448 | Half of all requests are currently refused and cost nothing.
Rows two and three are scenarios, not forecasts. Until the usage counter records what a request actually consumed, nobody can put a defensible number on what a real bid costs to run.

## Issues & actions
‹ Contents
# | Issue | What it means | Priority | Suggested next step | Owner | By when | Status
1 | Nobody is approving what the system produces | 1,367 items waiting, 8 approved, none rejected. Until that queue is worked, nothing the platform produces turns into a bid. | High | Find out whether this is staffing, training, or a screen people cannot find. |  |  | Not started
2 | Half the AI requests are blocked by our own privacy rule | 44 of 88 refused before reaching the AI. Anything unclassified is treated as confidential and cannot leave our servers. Correct behaviour, but it means the AI is barely exercised. | High | Decide the data-classification policy for ordinary tender documents. |  |  | Not started
3 | The cost and usage figures are not real | Every request records the same fixed usage regardless of the document. The cost total is arithmetic on that constant. | High | Do not budget from these figures. The engineering fix is one line per call site. |  |  | Not started
4 | Three stages never ran at all | Drawing take-off, drawing indexing and the technical narrative record zero activity on every attempt. Drawing measurements cannot be produced right now. | High | Confirm whether these are switched off or failing silently. |  |  | Not started
5 | Some jobs sit in a queue for hours | Programme jobs wait 37 hours on average before starting, procurement 26. The work itself takes seconds. | Medium | Check whether the queue worker is keeping up or stalling. |  |  | Not started
6 | Repeat work is not being reused | The reuse feature is switched off, so every request starts from scratch. | Medium | Turn on the response cache. Known outstanding item. |  |  | Not started
7 | Three measurements are not being recorded | How long each AI step took, how confident it was, and whether its output validated are all missing. | Low | Small change — the fields exist, they are simply not written. |  |  | Not started

## Test progress
‹ Contents
| Area | Tests | Pass | Fail | Blocked | Not started | % done | Note
| Test · Functional | 40 | 0 | 0 | 0 | 40 | 0%
| Test · Documents | 15 | 0 | 0 | 0 | 15 | 0%
| Test · Drawings | 12 | 0 | 0 | 0 | 12 | 0%
| Test · Tokens | 17 | 0 | 0 | 0 | 17 | 0%
| Test · Accuracy | 10 | 0 | 0 | 0 | 10 | 0%
| TOTAL | 94 | 0 | 0 | 0 | 94 | 0%
Sign-off
| Role | Name | Date | Decision
Test lead
Engineering lead
Product / manager

## Test · Functional
‹ Contents
ID | Module | Feature | What to do | What should happen | Priority | Result | What actually happened | Tester | Date | Notes / ticket
TEN-01 | TenderLogix | Tender upload | Upload a multi-file tender pack | All files accepted, listed and queued | High | Not started
TEN-02 | TenderLogix | Summary extraction | Open the tender stage | Client, reference, format and deadline all populated | High | Not started
TEN-03 | TenderLogix | Requirements | Check the requirement register | Each requirement listed with its source clause | High | Not started
TEN-04 | TenderLogix | Deadline override | Change the deadline by hand | Saved, and the change is on the audit trail | Medium | Not started
TEN-05 | TenderLogix | Bid / no-bid | Run bid qualification | A recommendation with reasons, awaiting a decision | Medium | Not started
DOC-01 | DocLogix | Register | Upload 10 mixed documents | All appear with type, revision and date | High | Not started
DOC-02 | DocLogix | Revisions | Upload a second revision | Superseded kept, latest marked current | High | Not started
DOC-03 | DocLogix | Transmittal | Issue to two recipients | Recorded with contents and recipients | Medium | Not started
DOC-04 | DocLogix | Revision compare | Compare two revisions | Differences listed clearly | Medium | Not started
DOC-05 | DocLogix | Search | Search a phrase inside a document | Document returned with the matching passage | Medium | Not started
DRW-01 | DrawLogix | Upload PDF | Upload a multi-sheet drawing PDF | Each sheet listed with its sheet number | High | Not started
DRW-02 | DrawLogix | Upload CAD | Upload a DWG or DXF | Layers and entities read; opens in the viewer | High | Not started
DRW-03 | DrawLogix | Drawing index | Check the index after processing | Entity and layer count populated for every sheet | High | Not started
DRW-04 | DrawLogix | Take-off | Run take-off on a known drawing | Measurements produced, each naming sheet and location | High | Not started
DRW-05 | DrawLogix | Measurement trace | Click a measurement | Drawing opens at the region it came from | High | Not started
DRW-06 | DrawLogix | BIM Studio draw | Ask for a simple floor plan | All requested elements placed, not just one | High | Not started
DRW-07 | DrawLogix | Revision compare | Upload a revised drawing | Changes between revisions highlighted | Medium | Not started
QNT-01 | QuantLogix | BOQ generation | Generate a bill from measurements | Lines produced, grouped, units normalised | High | Not started
QNT-02 | QuantLogix | Trace to source | Press Trace on a bill line | Measurement, sheet and layer shown | High | Not started
QNT-03 | QuantLogix | Correction cascade | Change a confirmed measurement | Downstream marked stale with a re-run list | High | Not started
QNT-04 | QuantLogix | Reconciliation | Compare to a supplied bill | Differences listed line by line | Medium | Not started
CST-01 | CostLogix | Rate application | Price a bill from the library | Every line priced; each rate names its origin | High | Not started
CST-02 | CostLogix | Rate override | Override one rate | Applied, original kept, change audited | High | Not started
CST-03 | CostLogix | Estimate build-up | Open the estimate | Bill, overheads, contingency and total, all adjustable | Medium | Not started
CST-04 | CostLogix | Export | Export the estimate | Opens in Excel with header details filled | Medium | Not started
SCH-01 | ScheduleLogix | Programme | Build from the bill | Activities with durations and dependencies | High | Not started
SCH-02 | ScheduleLogix | Critical path | Check the critical path | Critical activities drive the end date | High | Not started
SCH-03 | ScheduleLogix | Calendar | Set a Gulf working week | Durations recalculate | Medium | Not started
SCH-04 | ScheduleLogix | Baseline | Set then move a baseline | An unexplained move is refused | Medium | Not started
PRC-01 | ProcureLogix | Packages | Group bill lines into packages | Packages with value, lines and lead time | High | Not started
PRC-02 | ProcureLogix | Package trace | Open a package | The bill lines it covers are listed | Medium | Not started
NAR-01 | NarrativeLogix | Narrative | Generate the technical narrative | Draft from confirmed records only | Medium | Not started
PLT-01 | Platform | Login | Sign in as each role | Correct workspace and permissions | High | Not started
PLT-02 | Platform | Review queue | Confirm one, reject another | Both recorded against the tester's name | High | Not started
PLT-03 | Platform | Permission gate | Sign in without confirm rights | Button hidden; API refuses the same action | High | Not started
PLT-04 | Platform | Audit chain | Press Verify audit chain | Chain reports clean | High | Not started
PLT-05 | Platform | Tenant isolation | Open another tenant's project by ID | Refused; nothing returned | High | Not started
PLT-06 | Platform | Language | Switch to Arabic | Full RTL layout, same records and permissions | Medium | Not started
PLT-07 | Platform | Autopilot | Run a bid end to end | Every stage advances; start/stop/finish audited | Medium | Not started
PLT-08 | Platform | Blocked request | Process an unclassified document | Refused with a clear message, not silence | High | Not started

## Test · Documents
‹ Contents
ID | Size band | File used | Size MB | Pages | Target sec | Run 1 | Run 2 | Avg sec | Tokens in | Tokens out | Result | Tokens/page | Tester | Notes
DOC-A1 | < 0.5 MB |  |  |  | 10 | [5 empty] | Not started
DOC-A2 | < 0.5 MB |  |  |  | 10 | [5 empty] | Not started
DOC-A3 | < 0.5 MB |  |  |  | 10 | [5 empty] | Not started
DOC-B1 | 0.5 – 2 MB |  |  |  | 30 | [5 empty] | Not started
DOC-B2 | 0.5 – 2 MB |  |  |  | 30 | [5 empty] | Not started
DOC-B3 | 0.5 – 2 MB |  |  |  | 30 | [5 empty] | Not started
DOC-C1 | 2 – 8 MB |  |  |  | 90 | [5 empty] | Not started
DOC-C2 | 2 – 8 MB |  |  |  | 90 | [5 empty] | Not started
DOC-C3 | 2 – 8 MB |  |  |  | 90 | [5 empty] | Not started
DOC-D1 | 8 – 32 MB |  |  |  | 300 | [5 empty] | Not started
DOC-D2 | 8 – 32 MB |  |  |  | 300 | [5 empty] | Not started
DOC-D3 | 8 – 32 MB |  |  |  | 300 | [5 empty] | Not started
DOC-E1 | 32 MB + |  |  |  | 600 | [5 empty] | Not started
DOC-E2 | 32 MB + |  |  |  | 600 | [5 empty] | Not started
DOC-E3 | 32 MB + |  |  |  | 600 | [5 empty] | Not started
Today's live figures get FASTER as files get bigger — 3.9 s under 0.5 MB but 2.4 s above 32 MB. That is not credible; understand why before treating any of it as a baseline. Tokens per page is the column to watch: if it is flat across every band, the counter is still a placeholder.

## Test · Drawings
‹ Contents
ID | Complexity | Drawing used | Format | Sheets | Layers | Entities | Size MB | Target sec | Run 1 | Run 2 | Avg sec | Result | Tokens | Tester | Notes
DRW-SIM1 | Simple | [6 empty] | 30 |  |  |  | Not started |  |  | Single sheet, one discipline, under 500 entities
DRW-SIM2 | Simple | [6 empty] | 30 |  |  |  | Not started
DRW-SIM3 | Simple | [6 empty] | 30 |  |  |  | Not started
DRW-MED1 | Medium | [6 empty] | 120 |  |  |  | Not started |  |  | 2–5 sheets, 2–3 disciplines, 500–5,000 entities
DRW-MED2 | Medium | [6 empty] | 120 |  |  |  | Not started
DRW-MED3 | Medium | [6 empty] | 120 |  |  |  | Not started
DRW-CPX1 | Complex | [6 empty] | 600 |  |  |  | Not started |  |  | 6+ sheets, multi-discipline, over 5,000 entities
DRW-CPX2 | Complex | [6 empty] | 600 |  |  |  | Not started
DRW-CPX3 | Complex | [6 empty] | 600 |  |  |  | Not started
DRW-SCN1 | Scanned | [6 empty] | 300 |  |  |  | Not started |  |  | Raster PDF with no vector data at all
DRW-SCN2 | Scanned | [6 empty] | 300 |  |  |  | Not started
DRW-SCN3 | Scanned | [6 empty] | 300 |  |  |  | Not started
Record entities and layers for every drawing — they turn "it was slow" into "it was slow at 40,000 entities". The live system returns no entity or layer count at all today, so read them from the CAD file by hand.

## Test · Tokens
‹ Contents
ID | Step | What it does | Runs | Avg in | Avg out | Avg total | Target | Result | Cost / run | Worst run | Tester | Notes
TOK-01 | Reading documents | Sorts and splits the uploaded tender pack |  |  |  |  | 4000 | Not started
TOK-02 | Tender reading | Pulls summary, dates and requirements |  |  |  |  | 8000 | Not started
TOK-03 | Bid / no-bid decision | Recommends whether to pursue |  |  |  |  | 3000 | Not started
TOK-04 | Specification reading | Extracts clauses from the specification |  |  |  |  | 8000 | Not started
TOK-05 | Drawing indexing | Catalogues each drawing sheet |  |  |  |  | 3000 | Not started
TOK-06 | Drawing take-off | Measures quantities off the drawings |  |  |  |  | 12000 | Not started
TOK-07 | Bill of quantities | Turns measurements into bill lines |  |  |  |  | 6000 | Not started
TOK-08 | Pricing | Applies rates to the bill lines |  |  |  |  | 4000 | Not started
TOK-09 | Compliance checks | Checks the bid against requirements |  |  |  |  | 6000 | Not started
TOK-10 | Risk assessment | Flags risks on the bid |  |  |  |  | 4000 | Not started
TOK-11 | Programme / schedule | Builds the works programme |  |  |  |  | 6000 | Not started
TOK-12 | Procurement packages | Groups bill lines into packages |  |  |  |  | 4000 | Not started
TOK-13 | Technical narrative | Writes the technical submission |  |  |  |  | 10000 | Not started
TOK-14 | Proposal writing | Drafts the proposal document |  |  |  |  | 10000 | Not started
TOK-15 | Bid approval pack | Assembles the approval pack |  |  |  |  | 3000 | Not started
TOK-16 | Client clarifications | Drafts questions back to the client |  |  |  |  | 3000 | Not started
TOK-17 | Copilot answers | Answers questions people ask |  |  |  |  | 3000 | Not started
| TOTAL — one full bid |  |  |  |  | 0 | 97000 |  | 0
That total is the number the manager wants: the token cost of one complete bid, to multiply by bids per year. Targets in column H are first guesses — replace them once one real bid has been measured.

## Test · Accuracy
‹ Contents
ID | What is extracted | Test set used | In truth | Found | Correct | Wrong | Missed | Precision | Recall | F1 | Target recall | Result | Notes
ACC-01 | Tender requirements | One real tender, marked by an estimator | [7 empty] | #VALUE! | 90% | Not started
ACC-02 | Submission dates and format | Same tender | [7 empty] | #VALUE! | 95% | Not started
ACC-03 | Specification clauses | One spec, clauses marked by hand | [7 empty] | #VALUE! | 90% | Not started
ACC-04 | Document classification | 50 mixed documents, labelled by hand | [7 empty] | #VALUE! | 95% | Not started
ACC-05 | Drawing sheet index | One drawing set, sheets listed by hand | [7 empty] | #VALUE! | 95% | Not started
ACC-06 | Drawing measurements | One drawing measured by a QS | [7 empty] | #VALUE! | 90% | Not started
ACC-07 | BOQ line generation | Bill produced by hand from the same drawings | [7 empty] | #VALUE! | 85% | Not started
ACC-08 | Rate matching | Bill priced by hand from the same library | [7 empty] | #VALUE! | 90% | Not started
ACC-09 | Programme activities | Programme built by hand from the same bill | [7 empty] | #VALUE! | 80% | Not started
ACC-10 | Risk identification | Risks listed by a bid manager | [7 empty] | #VALUE! | 75% | Not started
What the columns mean
| In truth | How many there actually are, counted by a person.
| Found | How many the system returned.
| Correct | How many of those found were right.
| Precision | Of what it found, how much was right.
| Recall | Of what was there, how much it found.
| F1 | The two combined into one number.
Recall matters more than precision. A requirement the system invents gets caught in review; one it misses ends up in a contract nobody priced.

## Targets
‹ Contents
Measure | Proposed target | Today | Basis
Document < 0.5 MB | 10 sec | 3.9 sec | Comfortably met.
Document 0.5 – 2 MB | 30 sec | 10.5 sec | Met.
Document 2 – 8 MB | 90 sec | 9.4 sec | Met.
Document 8 – 32 MB | 300 sec | 5.4 sec | Suspiciously fast — verify.
Document 32 MB + | 600 sec | 2.4 sec | Faster than a small file. Not credible.
Drawing — simple | 30 sec | not measured | No timing recorded today.
Drawing — medium | 120 sec | not measured | No timing recorded today.
Drawing — complex | 600 sec | not measured | No timing recorded today.
Queue wait, any job | 60 sec | up to 37 hrs | Worst case is the programme step.
Tokens, one full bid | 90,000 | not measured | Sum of the step targets.
Cost, one full bid | $11.61 | $0.56 placeholder | 90,000 tokens at $0.129 / 1k.
Recall — requirements | 90% | not measured | A missed requirement is a priced risk.
Recall — measurements | 90% | not measured | Within ±2% on quantity.
Recall — BOQ lines | 85% | not measured | Against a hand-built bill.
Functional tests passing | 100% of High | not measured | High priority must all pass.

## Test data needed
‹ Contents
ID | What is needed | Why | Priority | Owner | Ready by | Notes
TD-01 | One complete real tender pack | Drives almost every functional and accuracy test | High
TD-02 | The priced bill that tender produced | Answer key for BOQ and rate accuracy | High
TD-03 | 3 documents at each of the 5 size bands | 15 files for the document sheet | High
TD-04 | 3 each simple / medium / complex / scanned drawings | 12 files for the drawing sheet | High
TD-05 | A drawing measured by a QS | Answer key for measurement accuracy | High
TD-06 | A specification with clauses marked up | Answer key for clause extraction | Medium
TD-07 | 50 mixed documents labelled by type | Answer key for classification | Medium
TD-08 | A programme built by hand from the same bill | Answer key for scheduling | Medium
TD-09 | A second revision of one drawing | Revision compare and the stale cascade | Medium
TD-10 | Test accounts for each role | Permission and review-queue tests | High

## Glossary
‹ Contents
What the terms mean
Term | What it means
AI request | One call from the platform to the AI, for one step of one bid.
Job | One unit of background work. A job may make one AI request, or none.
Blocked by privacy rule | The platform refused to send data to the AI because it was unclassified, and unclassified is treated as confidential. Working as designed.
Queue wait | How long a job sat waiting before it started running.
Waiting for approval | The AI produced a suggestion. Nothing joins the bid until a named person confirms it.
Repeat work reused | When the platform reuses an answer it already produced. Currently switched off.
System error | A genuine fault, as opposed to a deliberate refusal.
Tokens | The unit the AI charges in. Roughly three-quarters of a word each.
Usage figures | How much AI capacity a request consumed. Currently a fixed placeholder, so it cannot be used for cost.
Precision | Of what the system found, how much was actually right.
Recall | Of what was really there, how much the system found.