## Summary
Preckon — where we are
Live system, 27 August 2026.
Projects run | 6
Jobs completed | 228
AI requests | 88
Blocked by privacy rule | 44 | Half. Refused before reaching the AI.
Tokens used | 26040 | Placeholder figure — see note below.
Cost recorded | 3.36 | Not real spend. Do not budget from it.
Waiting for approval | 1367 | Work stops here.
Approved | 8 | Out of 1,367. None rejected either.
System errors | 2
Three things to decide
1. Who owns the approval queue. 1,367 items are waiting on a person.
2. Whether ordinary tender documents can be sent to the AI. Half our requests are currently refused by our own privacy rule.
3. Sign-off on the test plan and its targets.
Note on cost: every request records the same fixed usage regardless of the document — a 0.2 MB file and a 33 MB file both record 310 tokens. The breakdown is shaped correctly, but the dollar figures are not real yet.

## Cost
Tokens and cost
Left: by step. Right: by project. Both total 26,040 tokens and $3.36.
Step | Requests | Blocked | Tokens | Cost | % of cost | Project | Requests | Tokens | Cost | % of cost
Reading documents | 30 | 15 | 9300 | 1.2 | 35.71% | DV Quaters | 22 | 6820 | 0.88 | 26.19%
Copilot answers | 10 | 5 | 3100 | 0.4 | 11.9% | DV Quaters Demo | 20 | 6200 | 0.8 | 23.81%
Tender reading | 6 | 3 | 1860 | 0.24 | 7.143% | venkat1 | 18 | 5580 | 0.72 | 21.43%
Bill of quantities | 6 | 3 | 1860 | 0.24 | 7.143% | Sowbelly Gulch Project | 18 | 4340 | 0.56 | 16.67%
Compliance checks | 6 | 3 | 1860 | 0.24 | 7.143% | venkat02 | 8 | 2480 | 0.32 | 9.524%
Proposal writing | 6 | 3 | 1860 | 0.24 | 7.143% | Shruthi2 | 2 | 620 | 0.08 | 2.381%
Bid approval pack | 6 | 3 | 1860 | 0.24 | 7.143% | TOTAL | 88 | 26040 | 3.36 | 100%
Risk assessment | 4 | 2 | 1240 | 0.16 | 4.762%
Pricing | 4 | 2 | 620 | 0.08 | 2.381% | Rate: $0.129 per 1,000 tokens. Blocked requests cost nothing, so the real cost per completed request is about double.
Programme / schedule | 2 | 1 | 620 | 0.08 | 2.381%
Specification reading | 2 | 1 | 620 | 0.08 | 2.381%
Bid / no-bid decision | 2 | 1 | 620 | 0.08 | 2.381%
Client clarifications | 2 | 1 | 620 | 0.08 | 2.381%
Procurement packages | 2 | 1 | 0 | 0 | 0%
Drawing take-off | never ran | 0 | 0 | 0 | 0%
Drawing indexing | never ran | 0 | 0 | 0 | 0%
Technical narrative | never ran | 0 | 0 | 0 | 0%
TOTAL | 88 | 44 | 26040 | 3.36 | 100%

## Test plan
Test plan | [5 empty] | Pass | 0 | of 94 tests
94 tests. Filter by Type. Fill in the cream columns. | [5 empty] | Fail | 0
Type | ID | What to test | Target | Measured | Result | Tester | Date | Notes
Functional | TEN-01 | Upload a multi-file tender pack | All files accepted and queued |  | Not started
Functional | TEN-02 | Tender summary after processing | Client, ref, format, deadline populated |  | Not started
Functional | TEN-03 | Requirement register | Each requirement shows its source clause |  | Not started
Functional | TEN-04 | Change the deadline by hand | Saved and audited |  | Not started
Functional | TEN-05 | Run bid qualification | Recommendation with reasons |  | Not started
Functional | DOC-01 | Upload 10 mixed documents | All listed with type, revision, date |  | Not started
Functional | DOC-02 | Upload a second revision | Old kept, new marked current |  | Not started
Functional | DOC-03 | Issue a transmittal | Recorded with contents and recipients |  | Not started
Functional | DOC-04 | Compare two revisions | Differences listed |  | Not started
Functional | DOC-05 | Search a phrase in a document | Document returned with the passage |  | Not started
Functional | DRW-01 | Upload a multi-sheet drawing PDF | Each sheet listed with its number |  | Not started
Functional | DRW-02 | Upload a DWG or DXF | Layers and entities read; opens in viewer |  | Not started
Functional | DRW-03 | Drawing index after processing | Entity and layer counts populated |  | Not started
Functional | DRW-04 | Run take-off on a known drawing | Measurements name sheet and location |  | Not started
Functional | DRW-05 | Click a measurement | Drawing opens at that region |  | Not started
Functional | DRW-06 | Ask BIM Studio for a floor plan | All elements placed, not just one |  | Not started
Functional | DRW-07 | Compare a revised drawing | Changes highlighted |  | Not started
Functional | QNT-01 | Generate a bill from measurements | Lines grouped, units normalised |  | Not started
Functional | QNT-02 | Press Trace on a bill line | Measurement, sheet and layer shown |  | Not started
Functional | QNT-03 | Change a confirmed measurement | Downstream marked stale with re-run list |  | Not started
Functional | QNT-04 | Compare to a supplied bill | Differences listed line by line |  | Not started
Functional | CST-01 | Price a bill from the rate library | Every line priced, each rate sourced |  | Not started
Functional | CST-02 | Override one rate | Applied, original kept, audited |  | Not started
Functional | CST-03 | Open the estimate | Bill, overheads, contingency, total — adjustable |  | Not started
Functional | CST-04 | Export the estimate | Opens in Excel with header details |  | Not started
Functional | SCH-01 | Build a programme from the bill | Activities with durations and links |  | Not started
Functional | SCH-02 | Check the critical path | Critical activities drive the end date |  | Not started
Functional | SCH-03 | Set a Gulf working week | Durations recalculate |  | Not started
Functional | SCH-04 | Move a baseline | Unexplained move refused |  | Not started
Functional | PRC-01 | Group bill lines into packages | Packages with value, lines, lead time |  | Not started
Functional | PRC-02 | Open a package | Bill lines it covers are listed |  | Not started
Functional | NAR-01 | Generate the technical narrative | Draft from confirmed records only |  | Not started
Functional | PLT-01 | Sign in as each role | Correct workspace and permissions |  | Not started
Functional | PLT-02 | Confirm one item, reject another | Both recorded against your name |  | Not started
Functional | PLT-03 | Sign in without confirm rights | Button hidden and API refuses |  | Not started
Functional | PLT-04 | Press Verify audit chain | Chain reports clean |  | Not started
Functional | PLT-05 | Open another tenant's project | Refused, nothing returned |  | Not started
Functional | PLT-06 | Switch to Arabic | Full RTL, same records and permissions |  | Not started
Functional | PLT-07 | Run a bid on autopilot | Every stage advances, all audited |  | Not started
Functional | PLT-08 | Process an unclassified document | Clear refusal, not silence |  | Not started
Document | DOC-<1 | Process a document of < 0.5 MB — record seconds and tokens | under 10 sec |  | Not started
Document | DOC-<2 | Process a document of < 0.5 MB — record seconds and tokens | under 10 sec |  | Not started
Document | DOC-<3 | Process a document of < 0.5 MB — record seconds and tokens | under 10 sec |  | Not started
Document | DOC-01 | Process a document of 0.5 – 2 MB — record seconds and tokens | under 30 sec |  | Not started
Document | DOC-02 | Process a document of 0.5 – 2 MB — record seconds and tokens | under 30 sec |  | Not started
Document | DOC-03 | Process a document of 0.5 – 2 MB — record seconds and tokens | under 30 sec |  | Not started
Document | DOC-21 | Process a document of 2 – 8 MB — record seconds and tokens | under 90 sec |  | Not started
Document | DOC-22 | Process a document of 2 – 8 MB — record seconds and tokens | under 90 sec |  | Not started
Document | DOC-23 | Process a document of 2 – 8 MB — record seconds and tokens | under 90 sec |  | Not started
Document | DOC-81 | Process a document of 8 – 32 MB — record seconds and tokens | under 300 sec |  | Not started
Document | DOC-82 | Process a document of 8 – 32 MB — record seconds and tokens | under 300 sec |  | Not started
Document | DOC-83 | Process a document of 8 – 32 MB — record seconds and tokens | under 300 sec |  | Not started
Document | DOC-31 | Process a document of 32 MB + — record seconds and tokens | under 600 sec |  | Not started
Document | DOC-32 | Process a document of 32 MB + — record seconds and tokens | under 600 sec |  | Not started
Document | DOC-33 | Process a document of 32 MB + — record seconds and tokens | under 600 sec |  | Not started
Drawing | DRW-SIM1 | Process a simple drawing (1 sheet, 1 discipline, <500 entities) — record seconds, entities, layers | under 30 sec |  | Not started
Drawing | DRW-SIM2 | Process a simple drawing (1 sheet, 1 discipline, <500 entities) — record seconds, entities, layers | under 30 sec |  | Not started
Drawing | DRW-SIM3 | Process a simple drawing (1 sheet, 1 discipline, <500 entities) — record seconds, entities, layers | under 30 sec |  | Not started
Drawing | DRW-MED1 | Process a medium drawing (2–5 sheets, 500–5,000 entities) — record seconds, entities, layers | under 120 sec |  | Not started
Drawing | DRW-MED2 | Process a medium drawing (2–5 sheets, 500–5,000 entities) — record seconds, entities, layers | under 120 sec |  | Not started
Drawing | DRW-MED3 | Process a medium drawing (2–5 sheets, 500–5,000 entities) — record seconds, entities, layers | under 120 sec |  | Not started
Drawing | DRW-COM1 | Process a complex drawing (6+ sheets, >5,000 entities) — record seconds, entities, layers | under 600 sec |  | Not started
Drawing | DRW-COM2 | Process a complex drawing (6+ sheets, >5,000 entities) — record seconds, entities, layers | under 600 sec |  | Not started
Drawing | DRW-COM3 | Process a complex drawing (6+ sheets, >5,000 entities) — record seconds, entities, layers | under 600 sec |  | Not started
Drawing | DRW-SCA1 | Process a scanned drawing (raster PDF, no vector data) — record seconds, entities, layers | under 300 sec |  | Not started
Drawing | DRW-SCA2 | Process a scanned drawing (raster PDF, no vector data) — record seconds, entities, layers | under 300 sec |  | Not started
Drawing | DRW-SCA3 | Process a scanned drawing (raster PDF, no vector data) — record seconds, entities, layers | under 300 sec |  | Not started
Tokens | TOK-01 | Run reading documents five times — record average tokens | under 4,000 tokens |  | Not started
Tokens | TOK-02 | Run tender reading five times — record average tokens | under 8,000 tokens |  | Not started
Tokens | TOK-03 | Run bid / no-bid decision five times — record average tokens | under 3,000 tokens |  | Not started
Tokens | TOK-04 | Run specification reading five times — record average tokens | under 8,000 tokens |  | Not started
Tokens | TOK-05 | Run drawing indexing five times — record average tokens | under 3,000 tokens |  | Not started
Tokens | TOK-06 | Run drawing take-off five times — record average tokens | under 12,000 tokens |  | Not started
Tokens | TOK-07 | Run bill of quantities five times — record average tokens | under 6,000 tokens |  | Not started
Tokens | TOK-08 | Run pricing five times — record average tokens | under 4,000 tokens |  | Not started
Tokens | TOK-09 | Run compliance checks five times — record average tokens | under 6,000 tokens |  | Not started
Tokens | TOK-10 | Run risk assessment five times — record average tokens | under 4,000 tokens |  | Not started
Tokens | TOK-11 | Run programme / schedule five times — record average tokens | under 6,000 tokens |  | Not started
Tokens | TOK-12 | Run procurement packages five times — record average tokens | under 4,000 tokens |  | Not started
Tokens | TOK-13 | Run technical narrative five times — record average tokens | under 10,000 tokens |  | Not started
Tokens | TOK-14 | Run proposal writing five times — record average tokens | under 10,000 tokens |  | Not started
Tokens | TOK-15 | Run bid approval pack five times — record average tokens | under 3,000 tokens |  | Not started
Tokens | TOK-16 | Run client clarifications five times — record average tokens | under 3,000 tokens |  | Not started
Tokens | TOK-17 | Run copilot answers five times — record average tokens | under 3,000 tokens |  | Not started
Accuracy | ACC-01 | Tender requirements — compare against a hand-marked set, record % found | 90% or better |  | Not started
Accuracy | ACC-02 | Submission dates and format — compare against a hand-marked set, record % found | 95% or better |  | Not started
Accuracy | ACC-03 | Specification clauses — compare against a hand-marked set, record % found | 90% or better |  | Not started
Accuracy | ACC-04 | Document classification — compare against a hand-marked set, record % found | 95% or better |  | Not started
Accuracy | ACC-05 | Drawing sheet index — compare against a hand-marked set, record % found | 95% or better |  | Not started
Accuracy | ACC-06 | Drawing measurements — compare against a hand-marked set, record % found | 90% or better |  | Not started
Accuracy | ACC-07 | BOQ line generation — compare against a hand-marked set, record % found | 85% or better |  | Not started
Accuracy | ACC-08 | Rate matching — compare against a hand-marked set, record % found | 90% or better |  | Not started
Accuracy | ACC-09 | Programme activities — compare against a hand-marked set, record % found | 80% or better |  | Not started
Accuracy | ACC-10 | Risk identification — compare against a hand-marked set, record % found | 75% or better |  | Not started